| Issue History |  |  |  |
| --- | --- | --- | --- |
| Issue No. | Description of Change | Originator | Effective Date |
| 1 | Initial Release | Task Force | 01 MAY 2019 |

| REFERENCE DOCUMENTS |  |
| --- | --- |
| Document Number | Document Title |
| ISO 9001:2015 | Quality Management System-Requirements, clause 8.2.1 |
| EX-OM/EGD/001-014 | General & specific condition of contract |

| CONTENTS | Page No. |  | For Document Control Use Only |
| --- | --- | --- | --- |
| 1. Purpose | 1 |  |  |
| 2. Scope | 1 |  |  |
| 3. Process Owner | 1 |  |  |
| 4. Definitions and Abbreviations | 2 |  |  |
| 5. Procedure | 2 |  |  |
| 6.Recored | 6 |  |  |
| 7.Related documents | 7 |  |  |

1. PURPOSE

The purpose of this procedure is to develop effective means of claim handling process

2. SCOPE

This procedure applies to claim handling process of ASER Construction PLC.

3. Process owner

Engineering Department

4. Definitions& Abbreviations

4.1Definition

For the purpose of this documenting addition to the definition given in ISO 9000:2015 the following definitions apply

4.1.1 Cost escalation: revised cost of Contract Agreement when an appropriate claim is raised.

    - Time extension: an additional working time given by the client when the claim is insured.

4.2 Abbreviations

FLW = flow chart

ASER= ASER Construction PLC

OP=Operation procedure

EGD=Engineering department

5. Procedure

5.1. Process flow chart

| INPUT | PROCESS | OUTPUT | RESPONSIBLE |
| --- | --- | --- | --- |
| 1. Progress Report | Default Collect documents on defect due to delay on quality, cost Identify reason for default Write a letter to EGD/client/Consultant Submit to client/Consultant Ask time extension &price escalation Receive time extension & cost escalation approval 1. | 1.Delay Report | 1.Project Manager |
| 2.Delay Report | 2. | 2.Identified Reasons | 2.Project Manager |
| 3.Identified Reasons | 3. | 3.a. collected documents b. Defect Record | 3.Project Manager |
| 4.collected documents | 4. | 4. Letter a. EGD. b. client/Consultant | 4.Project Manager |
| 5.letter | No 5. Yes | 5.a. accepted letter b. responding letter | 5.client/consultant |
| 6.accepting letter | 6. | 6.Letter | 6.Engineering Dept. Staffs |
| 7.Letter | 7. | 7. maintain records | 7.Engineering Dept. Staffs |

5.2 Description of the process steps

| FLW | Process description |
| --- | --- |
| 1 2. 3. 4. 5. . | After the contract is signed a delay may occur in the site progress due to - Late possession of site - Late issue of drawings or design details - Unforeseen conditions - Shortage of construction material - Variations to the works - Late payment - Late supporting letter for customs clearance (if any) - And Late response to requests here the project manager should check project sites if everything is in accordance to the contract document & then he will go to get ready a delay report within a period described in the Contract Document. The project manager will revise the delay report to identify the reasons for delay. After the reasons are identified the project manager will collect documents & record major defects which support the letter will write to the EGD/client/consultant. The project manager will write an initiation letter to the Engineering department or directly to the client/consultant by referring the previous collected document. The client /consultant may accept the written letter or responding it to the Engineering department by referring an acceptable reason and the office can assure by letter of time extension & cost escalation. Finally, the Engineering department will receive the approved time extension or Cost escalation & then maintain it. |

6. Record

- Delay report

- Registered delay reasons

- Written letters

- Recorded defects due to delay

- Approved time extension & cost escalation letter

7. Related document

| Document No. | Document Title |
| --- | --- |
| OF/EGD/002 | Contractual Matters Report |
| OF/EGD/012 | Causes of Claim Follow-up |
| OF/EGD/013 | Site correspondence Follow-up |